## Team
Initials | First | Last | Email | GitHub Username
ac | Akanksha | Chatra | achatra@stevens.edu | akankshachatra
sk | Sravanthi | Kanchi | skanchi@stevens.edu | shravik
ssk | Saloni | Kalsekar | skalseka@stevens.edu | salonikalsekar
av | Achal | Vishwanath | aangarek@stevens.edu | achalav
|  |  | GitHub Repository: | CS555-SSW555_agileMethodologies

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US01 | Dates before current date | ssk | Done
1 | US02 | Birth before marriage | ssk | Done
1 | US03 | Birth before death | ac | Done
1 | US04 | Marriage before divorce | ac | Done
1 | US05 | Marriage before death | av | Done
1 | US06 | Divorce before death | av | Done
1 | US07 | Less then 150 years old | sk | Done
1 | US08 | Birth before marriage of parents | sk | Done
2 | US09 | Birth before death of parents | ssk | Done
2 | US10 | Marriage after 14 | ac | Done
2 | US11 | No bigamy | av | Done
2 | US12 | Parents not too old | sk | Done
2 | US13 | Siblings spacing | ssk | Done
2 | US14 | Multiple births <= 5 | ac | Done
2 | US15 | Fewer than 15 siblings | av | Done
2 | US16 | Male last names | sk | Done
3 | US29 | List deceased | ak | Done
3 | US30 | List living married | av | Done
3 | US31 | List living single | sk | Done
3 | US32 | List multiple births | ssk | Done
3 | US21 | Correct gender for role | ak | Done
3 | US22 | Unique IDs | av | Done
3 | US23 | Unique name and birth date | sk | Done
3 | US24 | Unique families by spouses | ssk | Done
4 | US25 | Unique first names in families | sk
4 | US26 | Corresponding entries | ak
4 | US27 | Include individual ages | av
4 | US28 | Order siblings by age | sk
4 | US18 | Siblings should not marry | ssk
4 | US35 | List recent births | ak
4 | US36 | List recent deaths | av
4 | US33 | List orphans | sk
ssk

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2017-09-19 | 32 |  | 0
Sprint 1 | 2017-10-03 | 24 | 8 | 1054 | 220 | 287.4545
Sprint 2 | 2016-07-17 | 16 | 8 | 1197 | 180 | 47.6667
Sprint 3 | 2016-07-17 | 8 | 8 | 1300 | 220 | 28.0909
Sprint 4 | 2016-07-31
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2017-09-19 | 32
2017-10-03 | 24 | 8 | 1054 | 220 | 287.5
2017-10-17 | 16 | 8 | 1197 | 180 | 47.7
2017-10-31 | 8 | 8 | 1300 | 220 | 28.0909
0

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates before current date | ssk | Done | 50 | 180 | 158 | 240 | Completed
US02 | Birth before marriage | ssk | Done | 120 | 60 | 148 | 180 | Completed
US03 | Birth before death | ac | Done | 80 | 120 | 88 | 120 | Completed
US04 | Marriage before divorce | ac | Done | 30 | 180 | 115 | 120 | Completed
US05 | Marriage before death | av | Done | 120 | 60 | 124 | 180 | Completed
US06 | Divorce before death | av | Done | 25 | 120 | 127 | 180 | Completed
US07 | Less then 150 years old | sk | Done | 30 | 120 | 151 | 240 | Completed
US08 | Birth before marriage of parents | sk | Done | 120 | 60 | 143 | 120 | Completed
Review Results
Keep doing:
Communicating with the team members
Updating the source code on regular basis
Avoid:
Integration at the last moment

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US09 | Birth before death of parents | SSK | done | 80 | 120 | 156 | 150 | Completed
US10 | Marriage after 14 | AC | done | 100 | 180 | 136 | 220 | Completed
US11 | No bigamy | AV | done | 80 | 120 | 159 | 120 | Completed
US12 | Parents not too old | SK | done | 70 | 120 | 163 | 120 | Completed
US13 | Siblings spacing | SSK | done | 100 | 120 | 167 | 120 | Completed
US14 | Multiple births <= 5 | AC | done | 100 | 180 | 130 | 180 | Completed
US15 | Fewer than 15 siblings | AV | done | 80 | 120 | 113 | 120 | Completed
US16 | Male last names | SK | done | 100 | 180 | 173 | 180 | Completed
Review Results
Keep doing:
Communicating with the team members
Updating the source code on regular basis
Avoid:
Eating too much !

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US29 | List deceased | AK | done | 150 | 220 | 123 | 130 | Completed
US30 | List living married | AV | done | 150 | 180 | 131 | 140 | Completed
US31 | List living single | SK | done | 130 | 120 | 158 | 160 | Completed
US32 | List multiple births | SSK | done | 150 | 220 | 155 | 160 | Completed
US21 | Correct gender for role | AK | done | 160 | 120 | 140 | 150 | Completed
US22 | Unique IDs | AV | done | 120 | 220 | 136 | 140 | Completed
US23 | Unique name and birth date | SK | done | 150 | 220 | 162 | 170 | Completed
US24 | Unique families by spouses | SSK | done | 150 | 180 | 147 | 150 | Completed
Review Results
Keep doing:
Communicating with the team members
Updating the source code on regular basis
Avoid:
Integrating the code at last moment

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US25 | Unique first names in families | sk |  | 180 | 220
US26 | Corresponding entries | ak |  | 150 | 180
US27 | Include individual ages | av |  | 130 | 220
US28 | Order siblings by age | sk |  | 170 | 220
US18 | Siblings should not marry | ssk |  | 160 | 120
US35 | List recent births | ak |  | 180 | 220
US36 | List recent deaths | av |  | 150 | 220
US33 | List orphans | sk |  | 150 | 180

## Stories
Story ID | Story Name | Story Description
` | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)